## INITIATIVE PROCESS

Once an Initiative has been vetted and approved by ELT

1. Strategy

• Discovery/Brainstorm Session:

Collaborative sessions to uncover opportunities, challenges, and innovative ideas

aligned with company objectives. The aim is to define high-level goals and how to

move forward.

2. Expectations

• Brief Build:

Create a concise, actionable document outlining scope, objectives, stakeholders,

deliverables, and success criteria.

• Project Management Board Build:

Establish a Monday.com board (or equivalent tool) with all actionable items,

timelines, and stakeholders clearly assigned.

◦ Use project management tools (e.g., Gantt charts or Monday.com) for real-

time tracking and automated reminders.

3. Plan

• Kickoff Meeting:

Officially launch the initiative by presenting the brief and project board. Align

stakeholders on goals, roles, KPIs, and timelines.

Suggestion: Incorporate risk assessment and a high-level opportunity evaluation

into this stage.

◦ Conduct a thorough assessment during the Kickoff Meeting or Plan Stage.

◦ Communication Plan (Document including Unique Slack channel etc)

◦ Training plan

• Meeting: Feedback Session #1 (Presentation of Initial Work) 1 week later:

Share initial drafts or plans with stakeholders for feedback. The focus is on

aligning deliverables with the strategic vision and refining outputs.

Suggestion: Leverage templates to standardize input collection for actionable

feedback.

◦ Success Criteria for Milestones: Tie milestones to KPIs set in the brief (e.g.,

“80% alignment with strategic goals at Feedback Session #1”).• Meeting: Feedback Session #2 (Revised Work) 2 weeks later:

Present refined work, addressing gaps or concerns. Focus on ensuring alignment

with overall strategy and goals.

4. Organize

• Meeting: Feedback Session #3 (Pre-Launch Flight Check/Approval) 3 weeks

later:

Conduct a thorough review to confirm all elements—resources, approvals, work,

and dependencies—are in place. Establish readiness for launch is at 100%.

5. Implement

• Launch:

Execute the initiative as planned. Monitor progress in real-time and address

issues as they arise. Use automated tools for notifications, dependencies, or

deadlines.

6. Measure

• Meeting: Post-Launch Review (Feedback Session #4):

Evaluate immediate outcomes against KPIs. Gather qualitative feedback (e.g.,

from stakeholders or customers) and implement immediate corrective actions.

• Depending on nature of initiative

• 1 week intervals for a few weeks

• Post-Mortem/Measurement (Final Meeting):

Analyze successes, challenges, and learnings. Document findings in a lessons-

learned repository to guide future projects. Conduct a team survey to capture

fresh insights.